# CAP V-SAR

## Civil Air Patrol Virtual Search and Rescue Trainer

## Implementation Plan

Electronic Search Trainer for Mission Pilots, Mission Observers,
Mission Scanners and Mission Base Staff

| Document | Implementation Plan, Version 0.7 (Draft) |
| --- | --- |
| Date | 5 September 2026 |
| Status | Draft for review - not yet approved for training use |
| Prepared for | Squadron / Wing Emergency Services Training Staff |

This document describes a training aid. It is not a certified flight training device and confers no training credit unless and until such credit is approved by the appropriate CAP authority.

### Revision history

| Ver | Date | Summary |
| --- | --- | --- |
| 0.1 | 2026-09-05 | Initial draft |
| 0.7 | 2026-09-06 | Corrected SET to Skills Evaluation Trainer - a member qualified to sign off tasks for qualification. Separated Exercise Instructors from SETs in Team C, since only a SET can confer credit. Sharpened the Stan/Eval question accordingly and added Section 12.9 on evidence for sign-off. |
| 0.6 | 2026-09-06 | Added Section 12, Project Organization and Roles: governance tier, three delivery teams, assurance and liaison roles, a phase-by-phase staffing table, honest time commitments for recruiting, single points of failure, meeting cadence, and sustainment controls. Added decisions for naming the Sponsor, Project Officer and deputies. |
| 0.5 | 2026-09-06 | Scenario C-1 rewritten to match the sortie as flown: 121.5 MHz beacon only, on the ground at the ESCON fix on the KCRQ ILS (3,300 ft on the plate), SoCal Approach protecting the approach altitude and issuing blocks above and below. Ramp false alert and the 406 beacon moved to variants. |
| 0.4 | 2026-09-06 | Added Section 6.7.4: a line item to approach Austin Meyer at Laminar Research for datarefs completing the copilot transmit path. Corrected 6.7.2 - X-Plane already models a full copilot audio panel including a copilot COM transmit selector; the actual gap is the ATC transmit path, which is smaller than v0.3 implied. Added the vendor engagement work item to the phase table, risks and decisions. |
| 0.3 | 2026-09-06 | Project named CAP V-SAR. Added PilotEdge live ATC as an optional layer (6.3). Added Scenario C-1, a coordinated ELT prosecution in Class D airspace with live ATC, drawn from an actual unit sortie (4.5). Added Mission Observer COM panel design and the split-COM constraint (6.7). Corrected 2.2 and 6.6: live ATC and inter-aircraft visibility are addressed when PilotEdge is used. Budget, risks and decisions updated. |
| 0.2 | 2026-09-05 | Red-team revision. Propagation engine relocated from Air Manager into a sim-side scripted plugin (terrain probing and networking are not available in Air Manager Lua). Added 406 MHz burst-cadence behaviour, scenario start conditions from AFRCC-style alerts, budget, measures of effectiveness, cadet-protection consideration, multi-aircraft visibility note. CalTopo Desktop API ingestion marked unverified. Isolation section reduced to its one real touchpoint. Effort revised to 45-75 developer-days. |

### Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Author |  |  |  |
| Squadron Emergency Services Officer |  |  |  |
| Wing Standardization / Evaluation |  |  |  |

# 1. Executive Summary

This plan describes a networked desktop simulator for training Civil Air Patrol aircrews and mission base staff in electronic search - locating 121.5 / 243 / 406 MHz distress beacons using an airborne direction finder. The system is entirely software: X-Plane 12, custom instruments, and internet-hosted services. Nothing in it transmits on real radio equipment or radiates a beacon signal.

The system consists of four layers: commercial flight simulation (X-Plane 12) hosting a scripted signal-propagation plugin; an instrument layer built in Air Manager 5 that replicates the Becker SAR-DF 517 and its successor the RHOTHETA RT-600; network services providing simulated radio communications and live position tracking; and a mission base client that displays the exercise on a CalTopo map.

The central technical insight is that X-Plane does not simulate distress beacons at all. This is an advantage rather than an obstacle: because the entire signal chain must be synthesized, the instructor gains complete control over the training scenario. Signal propagation effects that make electronic search difficult in the real world - radio horizon, terrain masking, the 50-second 406 MHz burst cadence, the cone of confusion over the beacon, multipath false bearings - can be introduced deliberately and repeatably.

The estimated effort is 45 to 75 developer-days across five phases, with a usable single-seat DF trainer at the end of Phase 2. The largest technical risks are in the integration boundaries and in artwork, not in the flight simulation. The largest non-technical risks are that the product is built without confirming what it will be permitted to be used for, and that nobody owns it after delivery.

### 1.1 Assumptions requiring confirmation

| Assumption | Basis | Impact if wrong |
| --- | --- | --- |
| Target aircraft is a Cessna 172 / 182 with G1000 | Standard CAP corporate fleet | Changes cockpit layout and whether the DF panel stands alone or sits beside a simulated G1000 |
| Both SAR-DF 517 and RT-600 are in scope | CAP is mid-transition between the two | Halves or doubles faceplate work; propagation engine is unaffected |
| Mission base staff participate remotely over the internet | Stated requirement | Drives the VPN and hosting design in Section 9 |
| A CalTopo team account is available or obtainable | Required for API credentials and Desktop licensing | Section 7 fallback options apply |
| Participants are senior members only | Not yet stated | Cadet participation in an online environment engages Cadet Protection requirements (Section 10) |
| Someone with graphics skills is available for faceplate artwork | Not yet identified | Artwork is a distinct skill from coding; without it, faceplates will be functional but unconvincing |

# 2. Background and Problem Statement

### 2.1 The training gap

Electronic search is a perishable skill that is expensive to practice. A training sortie requires an aircraft, fuel, a crew, a practice beacon, and suitable terrain. Weather and aircraft availability constrain scheduling. Most significantly, a real training sortie produces whatever signal conditions happen to exist that day - crews may fly an entire mission without encountering the specific failure modes that cause real searches to go wrong.

The consequence is that crews often first encounter a reciprocal bearing, a terrain-masked signal, or a needle that swings wildly on close approach during an actual mission. These are precisely the situations where a trained response matters most.

### 2.2 What a simulator can and cannot address

| Addressed well | Not addressed |
| --- | --- |
| DF equipment operation and mode selection under time pressure | Actual aircraft handling and airmanship |
| Search pattern discipline and navigation | Physical scanning out the window for wreckage |
| Interpreting ambiguous or degraded signals | Fatigue, turbulence, motion sickness, cockpit noise |
| Crew coordination and task division between MP, MO and MS | Real radio propagation (ATC interaction is addressed via PilotEdge - Section 6.3) |
| Mission base to aircrew communication and reporting discipline | Ground team interface and physical clue detection |
| Repeating a difficult scenario until the crew gets it right | Legal and regulatory currency requirements |
| Prosecuting a 406 alert from AFRCC-style initial data | Seeing other aircraft, unless all crews connect to PilotEdge (Section 6.6) |

### 2.3 Equipment and beacon context

The Becker SAR-DF 517 is a four-band precision direction finder that presents a bearing relative to the aircraft nose for signals on 121.5, 156.8, 243 and 406 MHz. It has a notable limitation: it detects only two of the eighteen 406 MHz channels in use today (406.025 and 406.028 MHz). CAP is consequently replacing the 517 with the RHOTHETA RT-600, which covers all 406 MHz channels.

Beacon behaviour matters as much as the receiver. A 406 MHz beacon transmits a short digital burst roughly every 50 seconds, and a DF operating on 406 can only update its bearing on each burst - between bursts it holds the last value. Most 406 beacons also transmit a continuous low-power homing signal on 121.5 MHz, and standard practice is to use the 406 bearing for the approach and switch to 121.5 for the final homing. Since 2009 the satellite system no longer monitors 121.5, so a 121.5-only ELT is typically found from a pilot report or airport report rather than a satellite alert. These differences define distinct scenario types (Section 4.4).

The design therefore separates the signal propagation engine from the instrument faceplate, so that both DF heads and all beacon types are driven by one shared model.

# 3. Training Objectives

The system shall enable a crew to demonstrate the following. These are written as observable behaviours so that they can later be mapped to CAP task requirements if training credit is pursued.

### 3.1 Mission Pilot

| Ref | Objective |
| --- | --- |
| MP-1 | Configure the DF for emergency or training frequencies, including selecting the mode within the power-up window |
| MP-2 | Fly an assigned search pattern at assigned altitude while managing DF interpretation |
| MP-3 | Execute a homing intercept from initial signal acquisition to overhead confirmation |
| MP-4 | Recognise and correct a reciprocal or multipath false bearing |
| MP-5 | Recognise the cone of confusion and use it to confirm station passage |
| MP-6 | Adjust altitude deliberately to manage radio horizon and terrain masking |
| MP-8 | Negotiate and fly a search in controlled airspace with live ATC, including block altitude requests and accommodating IFR arrival traffic |
| MP-7 | Work a 406 MHz beacon using burst-cadence bearings, then transition to 121.5 homing for the final approach |

### 3.2 Mission Observer and Mission Scanner

| Ref | Objective |
| --- | --- |
| MO-1 | Operate the DF head as a crew resource while the pilot flies |
| MO-2 | Maintain a bearing log and construct a position estimate from successive observations |
| MO-3 | Pass accurate, formatted position and status reports to mission base |
| MO-4 | Manage aural signal monitoring and squelch to detect a weak beacon |
| MS-1 | Maintain scan discipline and report sightings using correct clock-position phraseology |

### 3.3 Mission Base Staff

| Ref | Objective |
| --- | --- |
| MB-1 | Track sortie progress on a live map and maintain situational awareness of aircraft position |
| MB-2 | Receive, log and plot bearing observations reported by aircrew |
| MB-3 | Refine a search area from accumulating negative and positive information |
| MB-4 | Retask an airborne crew and confirm the retasking is understood |
| MB-5 | Maintain communications discipline across multiple simultaneous sorties |
| MB-6 | Open a search from an AFRCC-style 406 alert containing a position and uncertainty, and assign search areas accordingly |

### 3.4 Measures of effectiveness

A trainer with no measure of effect will be judged on how impressive it looks. The following are proposed as the basis for evaluating whether the system trains anything.

| Measure | Method |
| --- | --- |
| Time from first signal to overhead confirmation | Recorded automatically per sortie; trend across repeated scenarios per crew |
| Track efficiency | Distance flown after acquisition versus straight-line distance to beacon |
| False-bearing recovery | Time spent flying a reciprocal or multipath bearing before correction; scored by the instructor |
| Report accuracy | Position reports to base compared against recorded truth |
| Subject matter expert acceptance | Experienced MPs rate whether each injected effect behaves like the real thing (Phase 3 validation) |
| Transfer to the aircraft | Longer term: instructor assessment of crews on real practice-beacon sorties, before and after simulator use |

# 4. Concept of Operations

### 4.1 Operating modes

The system supports three escalating modes. Each is usable independently, and each successive mode adds infrastructure. This staging allows training value to be delivered early rather than waiting for the full network.

| Mode | Participants | Description | Requires |
| --- | --- | --- | --- |
| A - Solo | One trainee, optional instructor over the shoulder | Single workstation. Trainee flies and operates the DF. Instructor sets the beacon and injects signal effects from an instructor panel on the same machine. | Phase 2 |
| B - Crew | MP, MO, MS at separate stations | One simulator instance drives multiple Air Player displays. Crew coordinates internally over intercom. Instructor runs the scenario. | Phase 3 |
| C - Networked exercise | Multiple aircrews plus remote mission base staff | Several sim clients, simulated radio network, live tracking to a shared map. Mission base staff participate from home. Approximates a full exercise. | Phase 4-5 |

### 4.2 Roles and stations

| Role | Station | Function |
| --- | --- | --- |
| Mission Pilot (MP) | Sim client, primary display, yoke and rudder | Flies the aircraft, navigates the assigned pattern |
| Mission Observer (MO) | Air Player panel, second screen or tablet | Operates DF, logs bearings, works the radio to base |
| Mission Scanner (MS) | Air Player panel plus sim external view | Visual scan, reports sightings |
| Instructor / Exercise Controller | Instructor panel plus scenario service web UI | Places beacons, injects signal effects and equipment failures, adjudicates |
| Mission Base staff (IC, AOBD, MRO) | Browser-based mission base client, remote | Tracks aircraft, receives reports, retasks crews |

### 4.3 Representative training sortie

The following walkthrough illustrates Mode C with a 406 MHz beacon and defines the end-to-end behaviour the system must support.

| Step | Actor | Action |
| --- | --- | --- |
| 1 | Instructor | Selects a scenario: beacon type and location, transmit power, terrain profile, alert source, and any injected faults. Beacon location is hidden from all participants. |
| 2 | Mission Base | Receives a simulated AFRCC alert: 406 beacon, encoded or Doppler position with an uncertainty radius. Opens the training CalTopo map, plots the alert position and search area. |
| 3 | Aircrew | Briefs, starts the sim at the staging airfield, powers up the DF and selects Training Mode within the power-up window. |
| 4 | Aircrew | Departs. The sim bridge begins posting position to the training map; the aircraft symbol appears at mission base. |
| 5 | Mission Base | Assigns a search area around the alert position over the simulated radio net. Crew reads back. |
| 6 | System | As the aircraft climbs, the beacon crosses the radio horizon. On the next 406 burst the signal exceeds squelch and a bearing appears - then holds for 50 seconds until the next burst. |
| 7 | Aircrew | MO reports the first bearing. MP turns to home, understanding the needle will not move again until the next burst. Base plots the bearing. |
| 8 | System | On the scripted profile, a ridge produces a reflected signal and the next burst bearing shifts 40 degrees. The crew must recognise this rather than chase it. |
| 9 | Aircrew | Climbs for line of sight, re-acquires a stable bearing across two bursts, reports a corrected bearing. |
| 10 | Aircrew | Within a few miles, switches the DF to 121.5 and picks up the continuous homing signal. Needle now updates continuously and sensitivity increases. |
| 11 | System | Overhead, the cone of confusion is entered and the bearing becomes indeterminate. |
| 12 | Aircrew | Confirms station passage, reports coordinates to base. |
| 13 | Mission Base | Plots the find, marks it on the map, and closes the sortie. |
| 14 | Instructor | Reveals the true beacon position, replays the flight track against it, and debriefs. |

Step 14 is the point of the entire system. The recorded track replayed against ground truth is the highest-value training artefact the simulator produces, and it is something a real sortie provides only partially and at far greater cost.

### 4.4 Scenario start conditions

Real searches do not begin with a blank map. The scenario library should model the way the alert actually arrives, because it determines how mission base opens the search.

| Scenario type | Initial information | What it trains |
| --- | --- | --- |
| 406, GPS-encoded position | Position accurate to a few hundred metres | Rapid prosecution, confirmation, false-alert discipline |
| 406, Doppler position only | Position with uncertainty of several miles; possibly an ambiguous mirror solution | Search area planning; resolving ambiguity with a first bearing |
| 406 on a channel the 517 cannot receive | As above, but the DF shows nothing on 406 | Understanding equipment limits; falling back to 121.5 homer |
| 121.5 only, pilot report | An overflight report: heard on 121.5 near a position, no satellite data | Building a search area from a single weak datum |
| Airport false alert | 406 alert resolving to a hangar or ramp | Recognising and closing false alerts efficiently; the most common real-world case |
| Intermittent or dying beacon | Any of the above with a duty-cycled or fading transmitter | Patience; not abandoning a search on signal loss |

### 4.5 Scenario C-1: Coordinated ELT localisation on the Palomar ILS with live ATC

Rewritten in v0.5 to match the sortie as actually flown.

Premise. A 121.5 MHz ELT is transmitting from the ground at the ESCON fix on the ILS approach to McClellan-Palomar Airport (KCRQ), Carlsbad, California, where the approach plate calls for 3,300 ft. There is no satellite alert - 121.5 has not been satellite-monitored since 2009 - so the tasking arrives from reports of a signal in the CRQ approach area, with no position beyond that. The source sits directly beneath the final approach course, inside SoCal Approach's airspace.

Why this scenario exists. It is drawn from an actual sortie flown by the unit. SoCal Approach protected the 3,300 ft approach altitude and issued the aircraft block altitudes above and below it, so the search could proceed around arriving IFR traffic rather than through it. Its training value is not the beacon: a strong 121.5 signal on flat ground near an airport is not hard to localise. The value is that the search cannot be flown at all without continuous negotiation with a busy approach controller, on the final approach course itself, with the ideal search altitude occupied by traffic. This is the only scenario in the library where ATC is the primary constraint rather than background texture, and it is the situation most likely to defeat a crew that has only ever searched over open terrain.

#### Configuration

| Element | Setting |
| --- | --- |
| Mode | C (networked), or B (crew) with a single aircraft |
| PilotEdge coverage | ZLA. SoCal Approach and KCRQ tower positions staffed. |
| Advance coordination | Recommended for multi-aircraft or instructor-observed runs, so controller staffing matches the exercise. Single-aircraft runs need no notice. |
| Beacon | 121.5 MHz only. Ground level at the ESCON fix, full power, unobstructed. No 406 component. |
| Reference charts | FAA ILS or LOC RWY 24, McClellan-Palomar (KCRQ), and the San Diego-area VFR sectional. ESCON INT is the intermediate fix at I-CRQ 10.4 DME, charted at 3,300 ft; approach course 245 degrees; SOCAL APP CON 127.3 / 323.0. Instructors should brief from the current cycle. |
| Alert source | Reports of a 121.5 signal in the CRQ approach area; no satellite data, no position estimate. (Adjust to the actual tasking source if a closer match is wanted.) |
| Injected effects | Continuous 121.5 signal. Needle sensitivity rising on close approach. Mild multipath from terrain east of the field. Cone of confusion over the fix. No terrain masking - the difficulty is airspace, not propagation. |
| ATC behaviour | Controller protects 3,300 ft at ESCON for the ILS and issues a block above and a block below it. Use the actual altitudes issued on the real sortie if recalled; otherwise the instructor sets them in the brief to the controller. |
| Aircraft | C182T, G1000, Becker 517 or RT-600. MO station with second COM panel (Section 6.7) if implemented. |
| Mission net | Mumble channel, separate audio path from PilotEdge |
| Duration | 60-75 minutes including brief and debrief |

#### Execution

| Step | Actor | Action |
| --- | --- | --- |
| 1 | Instructor | Sets the scenario: 121.5 beacon on the ground at ESCON, truth hidden. Confirms PilotEdge positions are staffed and, for a coordinated run, that the controller is briefed to protect the approach altitude and offer blocks above and below. |
| 2 | Mission Base | Receives the tasking on the training CalTopo map: 121.5 signal reported in the CRQ approach area, no position. Plots the reports and notes immediately that any search will sit on the ILS final. |
| 3 | Mission Base | Briefs the crew over the mission net: search area, the expectation that ATC will protect the approach altitude, and the requirement to obtain coordination before entering. Suggests requesting blocks above and below rather than a single altitude. |
| 4 | Aircrew | Briefs and departs the staging field. MO powers up the DF, selects Training Mode inside the power-up window, and sets the 121.5 training frequency. |
| 5 | Aircrew | MP contacts SoCal Approach, requests flight following and advises of the SAR operation: a 121.5 ELT believed to be on or near the ILS final, and the need to manoeuvre around it at several altitudes. This transmission is the heart of the scenario. |
| 6 | ATC (live) | Controller protects 3,300 ft at ESCON for arriving traffic and issues a block above and a block below. The crew works with what is issued rather than what they hoped for. |
| 7 | System | Inside radio horizon the 121.5 needle is continuous. Signal strength rises steadily toward the fix; the multipath effect produces an intermittent bearing offset from terrain to the east. |
| 8 | Aircrew | Works the upper block first. MO takes bearing cuts across the approach course and logs them; reports to base; base plots the cuts, which converge on ESCON. |
| 9 | ATC (live) | An arrival on the ILS passes through 3,300 ft between the two blocks. Crew must remain in the assigned block regardless of where the needle points. On PilotEdge the arriving aircraft is visible. |
| 10 | Aircrew | Requests and receives the lower block once the arrival is clear. Descends; needle sensitivity rises; the cone of confusion appears over the fix. |
| 11 | Aircrew | Confirms station passage over ESCON, reports the beacon on the ground at the fix with coordinates, and recommends ground follow-up. |
| 12 | Mission Base | Marks the find, coordinates the ground follow-up, thanks SoCal via the crew, and closes the sortie. |
| 13 | Instructor | Reveals beacon truth. Replays the track against it, against the blocks issued, and against the timing of the ILS arrivals. |

#### What this scenario assesses

| Objective | Observable |
| --- | --- |
| MP-8 | Was the initial call to Approach clear about what SAR manoeuvring on the final actually requires? Did the crew ask for blocks above and below rather than a series of one-off deviations? |
| MP-2, MP-3 | Did the pilot fly an accurate search inside the assigned block and home cleanly once cleared into the lower one? |
| MP-4, MP-5 | Did the crew recognise the multipath offset for what it was, and use the cone of confusion to confirm passage rather than chase the needle? |
| MO-1, MO-3 | Did the MO keep DF work and bearing logging going while the pilot was occupied on the ATC frequency? Were reports to base accurate and timely? |
| MB-3 | Did base refine the estimate from converging cuts and anticipate the need for the lower block? |
| Discipline | Did the crew stay in the block when the needle pointed into the protected altitude? |
| Crew resource management | Did radio workload get divided, or did one person try to work ATC, the mission net and the DF at once? |

INSTRUCTOR NOTE

The most common failure in this scenario is not a DF error. It is a crew that treats ATC as an obstacle to be minimised: accepting restrictions passively, never explaining what they actually need, and flying a degraded search as a result. The second most common is a crew that drifts out of its block toward the needle. Controllers respond well to a crew that states its requirement plainly. Debrief the initial Approach call specifically, and overlay the track on the block boundaries.

#### Variants

| Variant | Change |
| --- | --- |
| C-1a - Ramp false alert | Beacon is an aircraft parked on the KCRQ ramp instead of at ESCON. The most common real-world outcome; converging cuts point at the field and the crew must recommend a ground check rather than orbit. |
| C-1b - Two aircraft | A second CAP aircraft works an adjacent area. Both are on PilotEdge, visible to each other and to the controller, forcing base to deconflict tasking. |
| C-1c - 406 beacon at ESCON | Same geometry with a 406 MHz beacon and 121.5 homer. Adds the 50-second burst cadence and the 406-to-121.5 transition to the airspace problem; a sub-variant uses a 406 channel the Becker 517 cannot receive. |
| C-1d - No advance coordination | Run during normal PilotEdge operations as a routine flight-following request. Tests whether the crew can obtain blocks from a controller who is not expecting them. |
| C-1e - Genuine target east of the field | Beacon is a downed aircraft in terrain east of KCRQ. Adds terrain masking to the airspace problem. |

# 5. System Architecture

### 5.1 Layered overview

| Layer | Components | Responsibility |
| --- | --- | --- |
| 1. Simulation | X-Plane 12 plus a scripted DF engine plugin, on each aircrew workstation | Flight model, terrain, aircraft position truth, signal propagation computation |
| 2. Instrument | Air Manager 5, Air Player, custom plugins | DF faceplates, controls, instructor panel display |
| 3. Services | Scenario service, tracking service, radio server | Beacon truth, position aggregation, voice comms |
| 4. Command | Mission base web client, CalTopo training instance | Common operating picture, reporting, debrief |

### 5.2 Why the engine lives in the simulator, not in Air Manager

Changed in v0.2.

Version 0.1 placed the propagation engine inside Air Manager as a Lua library. This does not survive scrutiny. Two of the effects that justify the project - terrain masking and scenario state delivered from a remote instructor - need capabilities Air Manager's Lua environment does not appear to provide: querying terrain elevation, and network access. X-Plane provides both to plugins: a terrain probe, and the ability to create custom datarefs that any external program (including Air Manager) can read.

The engine is therefore a scripted X-Plane plugin, recommended in Python via XPPython3, which requires X-Plane 12 and supports registering custom datarefs and terrain probing. It publishes datarefs such as cap/df/bearing, cap/df/signal and cap/df/valid. Air Manager subscribes to these exactly as it would to any stock dataref. The faceplates become a pure display-and-control layer, which is what Air Manager is good at.

The principle "the simulator remains unmodified" from v0.1 is replaced by "no compiled plugin": a scripted plugin needs no toolchain and is updated by copying a file.

### 5.3 Component inventory

| Component | Technology | Location | Notes |
| --- | --- | --- | --- |
| Flight simulator | X-Plane 12 | Each workstation | Installed on the development workstation |
| DF engine plugin | XPPython3 plugin | Each workstation | Propagation model, terrain probe, custom datarefs. The core IP of the project. |
| DF faceplate (517) | Air Manager plugin, Lua | Workstation | Reads cap/df/* datarefs; owns controls, pages, modes, audio |
| DF faceplate (RT-600) | Air Manager plugin, Lua | Workstation | Same datarefs, different head. Requires RT-600 documentation not yet gathered. |
| Instructor panel | Web UI on scenario service, plus optional Air Manager panel | Instructor station | Remote-capable; does not depend on the trainee's workstation |
| Scenario service | Python, FastAPI | Server | Authoritative beacon truth; scenario library; scoring |
| Sim bridge | Python, UDP | Each workstation | Bidirectional: reads position from X-Plane, writes scenario state into the engine's datarefs |
| Tracking service | Python, FastAPI, SQLite or Postgres | Server | Aggregates positions, relays to CalTopo, records tracks for debrief |
| Radio server | Mumble (mumble-server) | Server | Channel-per-frequency voice network |
| Mission base client | Web application | Browser, remote | Map view, bearing log, sortie status, retasking |
| Mapping | CalTopo training instance | SaaS or Desktop | See Section 7 |
| Overlay network | WireGuard or Tailscale | All participants | Avoids exposing training services to the public internet |

### 5.4 Principal data flows

#### Flow 1 - Aircraft position to the common operating picture

X-Plane 12 (UDP RREF subscription to position datarefs)

-> Sim bridge (workstation, Python)

-> Tracking service (server)

-> CalTopo position report API   [map symbol]

-> Mission base client (WebSocket) [live display]

-> Track recorder (database)      [debrief replay]

#### Flow 2 - Beacon truth to the direction finder

Scenario service (beacon: lat, lon, elevation, type, power, effects)

-> Sim bridge (polls scenario service)

-> X-Plane UDP DREF write into cap/scenario/* datarefs

-> DF engine plugin: bearing, LOS via terrain probe, signal, cadence

-> cap/df/* datarefs

-> Air Manager faceplate: needle, signal bar, audio tone

Beacon truth is delivered to the workstation only as dataref values, at runtime, and only while the scenario is running. There is no file on the trainee's machine to peek at, and the scenario service can withhold truth entirely until the instructor reveals it.

#### Flow 3 - Voice

Aircrew headset -> Mumble client -> Mumble server (channel = frequency)

-> Mission base staff clients

Radio panel (Air Manager) -> si_variable -> local agent -> Mumble channel switch

### 5.5 Design principles

| Principle | Rationale |
| --- | --- |
| Engine separate from faceplate | Two DF heads, one physics implementation. A third head later needs no engine work. |
| Server holds beacon truth | Trainees cannot discover the answer locally. Multi-aircraft exercises share one beacon. |
| No compiled plugin | A scripted plugin needs no toolchain and is version-controlled as plain text. |
| Everything recorded | Debrief quality is the product. Track, bearings, radio calls and reports are all logged with timestamps. |
| CalTopo training instance is separate from any operational account | The one place this system touches a tool used for real missions (Section 7.4). |

# 6. Subsystem Design

## 6.1 Direction finder propagation engine

This is the technical core of the project and the component that determines whether the trainer produces competent searchers or merely entertained ones.

### 6.1.1 Inputs

| Source | Type | Use |
| --- | --- | --- |
| sim/flightmodel/position/latitude | double | Aircraft position |
| sim/flightmodel/position/longitude | double | Aircraft position |
| sim/flightmodel/position/elevation | double | MSL altitude |
| sim/flightmodel/position/psi | float | True heading, for relative bearing |
| sim/flightmodel/position/magnetic_variation | float | True to magnetic conversion |
| Terrain probe (XPLM) | call | Elevation at sampled points along the aircraft-to-beacon path |
| cap/scenario/* (custom, written by the bridge) | various | Beacon position, elevation, type, power, active effects |

Stock dataref names must be confirmed against Resources/plugins/DataRefs.txt in the installed X-Plane 12 before coding.

### 6.1.2 Core computation

# great circle bearing from aircraft to beacon (Python, in the engine plugin)

def true_bearing(lat1, lon1, lat2, lon2):

dlon = radians(lon2 - lon1)

y = sin(dlon) * cos(radians(lat2))

x = cos(radians(lat1)) * sin(radians(lat2)) - sin(radians(lat1)) * cos(radians(lat2)) * cos(dlon)

return (degrees(atan2(y, x)) + 360) % 360

# what the needle shows: bearing relative to the nose

rel_bearing = (true_bearing(ac_lat, ac_lon, bcn_lat, bcn_lon) - ac_heading) % 360

# radio horizon in NM, using aircraft height above the beacon's own elevation

height_above_beacon_ft = ac_alt_msl_ft - bcn_elev_msl_ft

horizon_nm = 1.23 * sqrt(max(height_above_beacon_ft, 0))

### 6.1.3 Signal model and injectable effects

Each effect below is individually switchable by the instructor. This catalogue is effectively the syllabus - each entry is a discrete teachable failure.

| Effect | Model | Trains |
| --- | --- | --- |
| Range attenuation | Free-space path loss; signal strength falls with distance | Reading signal strength as a range cue; managing squelch |
| Radio horizon | Signal is zero beyond 1.23 x sqrt(height above beacon, ft) NM | Deliberate altitude selection; why search altitude matters |
| Terrain masking | Probe terrain at intervals along the path; attenuate when the line of sight is blocked | Recognising a valley null; repositioning rather than concluding "no beacon" |
| 406 burst cadence | Bearing updates only on each burst, nominally every 50 seconds; holds between bursts | Patience with the 406 needle; planning turns around the next burst; knowing when to switch to 121.5 |
| 121.5 homer | Continuous, lower-power signal co-located with the 406 beacon; shorter horizon | The 406-to-121.5 transition on final approach |
| Cone of confusion | Bearing becomes indeterminate within a cone above the beacon | Confirming station passage; not chasing the needle overhead |
| Multipath / reflection | Inject a phantom bearing offset when geometry favours a reflecting ridge | The single most valuable scenario: recognising a false bearing |
| Needle sensitivity | Angular rate increases as range decreases | Damping pilot response on close approach |
| Intermittent beacon | Duty-cycle the transmission or fade it over time | Patience; not abandoning a search on signal loss |
| Wrong channel | Beacon transmits on a 406 channel the 517 cannot receive | Understanding the 517's limitation and why the RT-600 replaces it |
| Aural signature | Play the swept-tone warble on 121.5, volume scaled by signal strength | Aural acquisition, which is how weak beacons are often first detected |

The multipath, terrain and burst-cadence effects are what justify building this at all. Everything else can be approximated with a whiteboard.

## 6.2 Instrument faceplates

Air Manager plugins are ordinary folders on disk containing info.xml, logic.lua, preview.png, a lib/ directory and a resources/ directory for images and sounds. With the engine in the sim, the faceplate's Lua handles controls, display pages, the mode-selection window, squelch gating, brightness and audio - and reads cap/df/* for bearing and signal.

### 6.2.1 Becker SAR-DF 517 control mapping

| Ctl | Control | Simulated behaviour |
| --- | --- | --- |
| 1 | On/Off push button | Power state; starts the 10-second mode-selection window |
| 2 | Page select knob | Cycles display pages; also selects Emergency or Training mode during power-up window |
| 6 | Change frequency knob | Steps through the four configured frequencies on page 1 |
| 7 | Brightness button | Display brightness; held with page knob per the operating procedure |
| 8 | Store button | Commits MHz and kHz values when programming training frequencies on page 6 |
| 9 | Clear button | Clears entry |
| 10 | Squelch level knob | Sets the threshold arrow; gates bearing validity and audio |
| 11 | +/- knob | Field selection when programming; volume in normal operation |
| - | Display | Bearing pointer, signal level bar, page number, selected frequency |

The Emergency versus Training mode selection is available only in the first ten seconds after power-up. This is exactly the sort of procedural trap worth drilling repeatedly on the ground, and it costs nothing to rehearse in a simulator.

### 6.2.2 RHOTHETA RT-600

Built as a second faceplate against the same engine. Its full 406 MHz channel coverage is modelled, allowing side-by-side scenarios that demonstrate why the fleet is transitioning. Dependency: RT-600 operating documentation has not yet been gathered; the control mapping cannot be written until it is.

### 6.2.3 Artwork

Added in v0.2.

Faceplate images, knobs, bezels, needles and display fonts are graphics work, not code. Version 0.1 did not budget for it. Options, in decreasing order of fidelity: photograph and clean up the real unit; trace it as vector art; or build a functionally equivalent panel that is clearly not a copy of the vendor's. The third option also removes the likeness question in Section 10 if the product is ever shared. Estimated 3 to 6 days per head for someone with the skill; unbounded for someone without it.

## 6.3 Radio networks

Revised in v0.3.

The system uses two independent voice networks, mirroring the real aircraft: an ATC network and a CAP mission network. They are separate services, separate audio paths and separate push-to-talk keys.

### 6.3.1 ATC network - PilotEdge

PilotEdge provides live human controllers working to FAA Order 7110.65. It is optional but strongly recommended: it closes the "no real ATC" gap in Section 2.2 and makes scenarios such as C-1 possible at all.

| Aspect | Detail |
| --- | --- |
| Platform support | X-Plane 12 on Windows, macOS 12+ and Linux, including Steam. Confirmed on the vendor's How it Works page. |
| Coverage | Two areas. ZLA - Los Angeles ARTCC: half of California, much of Nevada, parts of Arizona and Utah. Western US - Seattle, Oakland, Salt Lake City, Denver and Albuquerque ARTCCs. Together roughly half the contiguous United States. |
| Hours | 8am to 11pm US Pacific, 7 days a week, guaranteed within the coverage area |
| Trial | 5 hours free, name and email only |
| SAR operations | Coordinated SAR manoeuvring and declared emergencies are welcomed by controllers and are established practice on the network. The unit has prior experience of both. |
| Traffic | All connected aircraft share one network and see each other, including third-party subscribers unrelated to the exercise |
| Discipline | Mission traffic - bearings, beacon reports, base coordination - stays on the CAP mission net rather than ATC frequencies. This matches real practice and keeps the ATC channel usable. |

### 6.3.2 CAP mission network - Mumble

Recommended platform: Mumble, self-hosted. It is open source, low latency, supports a channel hierarchy with access control, and exposes an RPC interface for automation.

| Design element | Approach |
| --- | --- |
| Frequency model | One Mumble channel per simulated frequency. Selecting a frequency on the radio panel moves the client into the corresponding channel. |
| Panel integration | Air Manager radio panel writes the selected frequency to a shared variable; a small local agent moves the Mumble client accordingly. |
| Intercom | A separate always-on channel per aircraft for internal crew coordination. |
| Recording | Server-side recording for debrief, with participant notification. |
| Range limiting | Revised. v0.1 proposed muting pairs of users beyond simulated radio range. Mumble has no native pairwise mute, so this is not a configuration task. The realistic options are: (a) skip it; (b) use Mumble's positional audio, feeding aircraft position from the bridge so voice attenuates with distance within a channel - an experiment, not a commitment; (c) build it into a custom voice layer later. Recommendation: (a) for Phase 5. |

Phasing note. A first useful version is simply a Mumble server with manually-joined channels named for the frequencies in use. Do not let radio realism block Phase 5.

### 6.3.3 Audio routing

Both networks run simultaneously on each station. PilotEdge uses the operating system's default communications device; Mumble must be bound explicitly to a different device or mixed deliberately. Each network needs its own push-to-talk key. This is per-station configuration work and belongs in a setup checklist rather than being rediscovered by every participant.

## 6.4 Sim bridge and flight tracking

### 6.4.1 X-Plane interface

Revised in v0.2.

X-Plane exposes a documented UDP protocol on port 49000. Two message types matter here: RREF, which subscribes to any dataref by name at a chosen rate and receives values back, and DREF, which writes a value into any writable dataref. The bridge uses RREF to read position and DREF to push scenario state into the engine's custom datarefs. This is preferable to the Data Output panel proposed in v0.1: nothing needs to be configured in the sim's settings, exact dataref names are used rather than opaque data-set indices, and the same channel carries data in both directions.

### 6.4.2 Tracking service

| Function | Detail |
| --- | --- |
| Ingest | Accepts position reports from each bridge, authenticated per exercise; two-to-five-second cadence, matching real tracking rather than sim frame rate |
| Fan-out | Pushes to the mission base client over WebSocket; forwards to CalTopo |
| Recording | Persists full track history per sortie for debrief replay |
| Ground truth overlay | Holds beacon position, revealed to the debrief view only after sortie close |
| Scoring | Computes the measures in Section 3.4 |

## 6.5 Mission base client

A browser application served by the tracking service, so that remote staff need install nothing. Minimum viable feature set:

| Feature | Purpose |
| --- | --- |
| Live map with aircraft symbols | Situational awareness (MB-1) |
| Alert intake | Presents the scenario's simulated AFRCC alert to open the search (MB-6) |
| Bearing log entry | Staff enter bearings reported by radio; the client draws the line (MB-2) |
| Sortie status board | Which aircraft, which area, fuel and time remaining |
| Retasking message | Text channel to supplement voice, and a record for debrief (MB-4) |
| Debrief replay | Scrub the recorded track against revealed beacon truth |

## 6.6 Multiple aircraft

Added in v0.2.

Revised in v0.3.

In Mode C each workstation runs its own copy of X-Plane. Without PilotEdge, crews see each other on the mission base map and hear each other on the mission net, but not out the window.

With PilotEdge this changes. All connected aircraft share one network and appear to each other as traffic, and to the controller. Two CAP aircraft working adjacent areas can be deconflicted by ATC exactly as they would be in reality, which is what makes variant C-1b possible. The trade is that the shared world also contains unrelated third-party subscribers.

Full shared-cockpit operation - MO and MS occupying the pilot's aircraft from separate machines - is a distinct capability. PilotEdge sells discounted network access for additional occupants (Section 9.4), but the shared-cockpit mechanism itself is provided by X-Plane or a third-party tool, not by PilotEdge. Confirm before relying on it.

## 6.7 Mission Observer COM panel

Added in v0.3.

In the aircraft the observer is not a passenger on the radios. The requirement is to give the MO station an independent radio control head, so that radio workload can be divided the way it is in the real aeroplane, and so that the MO is not reaching across the simulated cockpit to do what they do from their own seat in flight.

### 6.7.1 The panel itself is straightforward

An Air Manager COM panel for the MO station is among the easier instruments in this project. The relevant X-Plane interfaces are well established:

| Interface | Use |
| --- | --- |
| sim/cockpit2/radios/actuators/com2_frequency_hz_833 | COM2 active frequency, integer Hz, 8.33 kHz capable. Readable and writable. |
| sim/cockpit2/radios/actuators/com2_standby_frequency_hz_833 | COM2 standby, for flip-flop behaviour |
| sim/cockpit/switches/audio_panel_out | Transmit selection. 6 = COM1 transmits, 7 = COM2 transmits. This is the dataref PilotEdge reads to decide which radio it transmits on. |
| Commands "Transmit audio: COM1" / "Transmit audio: COM2" | The stock audio panel changes the receive selection only. Changing the transmit radio requires triggering these commands. |

Air Manager writes datarefs and issues commands directly, so the MO panel is a frequency display, a flip-flop control, a tuning knob and a transmit-select button. A day or two of work.

A documented pitfall: many third-party aircraft audio panels do not update audio_panel_out correctly, and this is a common cause of "cannot transmit on COM2" reports on PilotEdge. Whichever aircraft model is adopted must be verified against this dataref during Phase 0.

### 6.7.2 The constraint: split COM

Revised in v0.4 after inspecting the X-Plane dataref list.

The real GMA 1347 audio panel in the G1000 stack supports a split-COM mode in which the pilot transmits on one radio and the right seat transmits on the other simultaneously.

The picture in X-Plane is better than v0.3 stated. The simulator already models a complete copilot audio panel - roughly thirty datarefs covering copilot-side receive selection, per-source volumes and marker/DME audio - and it exposes a copilot COM transmit selector, audio_com_selection_man_copilot. The legacy sim/cockpit/switches/audio_panel_out is a single value, but it is not the whole story.

What appears to be missing is not the audio panel; it is the transmit path. The ATC-facing datarefs are single-crew: sim/atc/com1_tx and com2_tx are documented as "the pilot's voice", sim/atc/user_aircraft_transmitting is one boolean for the aircraft, and the plugin hooks sim/atc/com1_tx_override and com2_tx_override have no copilot equivalent. So a copilot audio panel selection exists, but there is no way to express "the copilot is transmitting on COM2 while the pilot transmits on COM1" to a plugin such as PilotEdge.

Conclusion: simultaneous split-COM transmit should still be assumed not to work until demonstrated - but the gap is a small asymmetry in an existing subsystem, not a missing feature. That materially improves the odds of Section 6.7.4 succeeding.

### 6.7.3 Three options

| Option | Description | Assessment |
| --- | --- | --- |
| A - MO works COM2 to ATC | MO panel tunes and transmits on COM2. Pilot and MO hand the transmit selection back and forth. | Works today, sequentially. Trains radio division without needing split COM. Start here. |
| B - MO works the CAP FM mission radio | MO panel represents the aircraft's VHF-FM mission radio; its audio routes to the Mumble mission net rather than to PilotEdge. | Recommended as the primary design. Matches how the crew actually divides radios on a sortie, needs no split COM, and creates no contention with PilotEdge. |
| C - True simultaneous split COM | Pilot on COM1 to ATC, MO on COM2, both live at once. | Requires a mechanism the stock dataref does not provide, plus shared-cockpit behaviour that needs testing. A Phase 5 investigation and a good question to put to PilotEdge directly. |

Options A and B together reproduce the real division of labour closely: the MO owns the mission net continuously and takes the ATC radio when the pilot's workload demands it. That is achievable with no unknowns and should be built before anyone attempts option C.

### 6.7.4 Line item: X-Plane dataref request to Laminar Research

Added in v0.4.

Work item. Approach Austin Meyer at Laminar Research to request a small set of datarefs completing the copilot transmit path, removing the split-COM limitation in Section 6.7.2. The unit has an existing relationship with him and he has been receptive to working with us previously.

Sequence matters. Do not open with a feature request. Establish first what the existing datarefs already do, so the request is a precise delta rather than an ask for something already shipped.

| Step | Action | When |
| --- | --- | --- |
| 1 | Test audio_com_selection_man_copilot in X-Plane 12: does setting it change anything observable in the transmit path, and does PilotEdge respond to it? | Phase 0 |
| 2 | Test whether com1_tx_override / com2_tx_override can be driven independently by two clients in a shared-cockpit configuration. | Phase 3 |
| 3 | Confirm with PilotEdge which datarefs their plugin actually reads for transmit selection, and what they would need to support a second transmitting crew position. | Phase 3 |
| 4 | Write the request as a one-page specification with the CAP use case, the gap table below, and an explicit offer to test pre-release builds. | Phase 3 |
| 5 | Send to Austin Meyer directly, copying the PilotEdge position from step 3 if they are willing to support the request. | Phase 3-4 |
| 6 | If accepted, validate in a beta build and report results. If declined or deferred, fall back to Section 6.7.3 options A and B, which lose no training value. | Phase 5 |

#### What already exists

| Dataref | Status |
| --- | --- |
| audio_selection_com1_copilot / _com2_copilot | Present, writable - copilot receive selection |
| audio_volume_com1_copilot / _com2_copilot | Present, writable - copilot audio levels |
| audio_selection_com_auto_copilot | Present, writable |
| audio_com_selection_man_copilot | Present, writable - copilot COM transmit selector, 6=com1, 7=com2 |
| sim/operation/sound/radios_are_copilot | Present but read-only - which audio jack the headset is in |
| sim/atc/com1_tx_override / com2_tx_override | Present, writable - but pilot-only |

#### Proposed additions

| Proposed dataref | Type | Purpose |
| --- | --- | --- |
| sim/atc/com1_tx_copilot sim/atc/com2_tx_copilot | int, read | Is the copilot position currently transmitting on COM1 / COM2. Mirrors the existing pilot-side datarefs. |
| sim/atc/com1_tx_override_copilot sim/atc/com2_tx_override_copilot | int, write | Lets a plugin declare that it is transmitting voice from the copilot position. This is the single most important item: without it, no plugin can represent two simultaneous transmitters. |
| sim/cockpit2/radios/actuators/audio_com_selection_copilot | int, write | Copilot equivalent of audio_com_selection, completing an existing asymmetry - the copilot side currently has only the legacy _man variant. |
| sim/operation/sound/radios_are_copilot | make writable | Allow a panel or plugin to bind the local user to the copilot audio position rather than only reporting it. |

FRAMING THE REQUEST

Three points make this credible. First, it completes a subsystem Laminar has already built rather than asking for new capability. Second, the use case is public-service search and rescue training for a USAF auxiliary, not a convenience feature. Third, multi-crew cockpits are a general need - airline, military and training customers all want two transmitting positions, so CAP V-SAR is a concrete instance of a broader gap. Offer to test, and be specific that options A and B mean the project is not blocked either way. A request that does not hold a vendor hostage is easier to say yes to.

# 7. CalTopo Integration

CalTopo integration is feasible and well supported for cloud-hosted maps. There are two distinct integration surfaces, and the plan uses both.

### 7.1 Choosing a test instance

| Option | Description | Assessment |
| --- | --- | --- |
| Separate training team account | A distinct CalTopo team account used only for exercises, with its own service-account API credentials. | Recommended for Phase 4. Every integration surface is known to work against the cloud service. Isolation depends on credential discipline. |
| CalTopo Desktop | A downloadable local HTTP server at localhost:8080 that syncs with an account. Team subscriptions include it and permit self-hosting. | Revised. Attractive for isolation, but it is not confirmed that the position-report API and Team API are served by a Desktop instance rather than only by caltopo.com. Desktop is documented to ingest locally-received radio (APRS) traffic, which suggests some local locator support, but that is not the same thing. Treat as a Phase 4 spike (Section 8), not a plan dependency. |
| Training maps in the operational account | Exercise maps created inside the live team account. | Not recommended. See 7.4. |

### 7.2 Position reporting

CalTopo supports live tracks from inReach, APRS, ADS-B and custom integrations. A custom source is configured in the map as a locator of type "Live Track - Fleet, Email, Other", which yields a reporting endpoint of the general form:

https://caltopo.com/api/v1/position/report/<connect-key>?id=<callsign>&lat=<lat>&lng=<lon>

The tracking service issues one HTTP request per aircraft per reporting interval. Elevation and aircraft-specific properties are also supported. Exact parameters must be confirmed against the endpoint provided when the locator is created.

### 7.3 Team API for map objects

Richer integration - creating markers for the alert position and the find, drawing search assignments, backing up exercise maps - uses CalTopo's supported Team API:

| Aspect | Detail |
| --- | --- |
| Account model | Service accounts created from the Team Admin page; they cannot be logged into interactively |
| Credentials | A credential ID sent with each request and a secret used only for signing. The secret is displayed once at creation and cannot be retrieved later. |
| Authentication | HMAC-SHA256 signature over method, URL, expiry and payload, with an expiry in epoch milliseconds |
| Capabilities | Account data, map create and delete, map data retrieval, map object management, photo import |
| Requirement | A team account is required to obtain credentials |

For map object manipulation there is also caltopo_python (from NCSSAR), a community Python interface to the unofficial API surface. The supported Team API is preferred where it covers the need.

### 7.4 Separation from operational CalTopo

Reduced in v0.2.

This system is entirely software. It does not key a real radio, radiate a beacon, or connect to AFRCC. The single place it touches a tool that is also used for real missions is CalTopo, and that is where the separation controls belong:

- Exercise mapping uses a training team account (or a verified Desktop instance) that shares no credentials with any operational account.

- API credentials for the training instance are stored separately and never reused.

- Simulated aircraft use callsigns that cannot be confused with CAP flight numbers, for example a SIM prefix, and exercise maps carry an exercise identifier in the title.

Voice-net "EXERCISE" phraseology is retained as good habit, not as a control - there is no real net for it to protect.

# 8. Implementation Phases

Effort figures are rough estimates in developer-days for one experienced developer, and should be treated as planning ranges rather than commitments. Artwork is listed separately because it is a different skill and usually a different person.

| Phase | Scope | Deliverable and exit criteria | Effort |
| --- | --- | --- | --- |
| 0 | Foundation | X-Plane 12 installed and flying. Air Manager 5 installed and licensed. Air Manager reading live datarefs. XPPython3 installed and a trivial plugin publishing a custom dataref that Air Manager can read. A stock instrument cloned, placed under git, and modified. Exit: a value set by our own plugin visibly moves a needle in Air Manager. | 3-5 days |
| 1 | Propagation engine | XPPython3 plugin computing bearing, range, radio horizon, terrain line-of-sight and signal strength from a hard-coded beacon; publishing cap/df/*. Validated against hand-calculated values and against a known terrain shadow. Exit: bearings correct within 1 degree at test points; a valley null appears where the map says it should. | 6-10 days |
| 2 | SAR-DF 517 faceplate and Mode A | Working 517 instrument with all controls, display pages, mode selection window, squelch and audio. Local instructor control of beacon placement via the bridge. Exit: a trainee can fly a complete homing intercept solo. | 8-12 days + artwork 3-6 |
| 3 | Effects library, RT-600, Mode B, validation | Full effects catalogue including 406 cadence and 121.5 homer. RT-600 faceplate (subject to documentation). Air Player crew stations. Validation session with two or more experienced Mission Pilots rating each effect against the real thing; tuning from their feedback. Exit: instructor reproduces a multipath false bearing on demand; a three-person crew runs a sortie; SMEs sign off the effects table. | 9-13 days + artwork 3-6 |
| 4 | Tracking and mapping | Spike first: confirm whether CalTopo Desktop serves the position-report and Team APIs; choose Desktop or training account accordingly. Then: bidirectional sim bridge, scenario service, tracking service, CalTopo live symbols, basic mission base map client with alert intake. Exit: a remote observer watches a sortie in real time on a training map that opened from a simulated alert. | 9-15 days |
| 5 | Radio net, mission base client, debrief | Mumble server and channel integration, full mission base client with bearing log and retasking, recorded debrief replay against ground truth, scoring per Section 3.4. Exit: a full Mode C exercise with remote base staff, followed by a track-versus-truth debrief. | 10-18 days |
| P | Parallel: vendor engagement | Test the existing copilot audio datarefs (Phase 0), confirm PilotEdge behaviour (Phase 3), then send a one-page dataref specification to Austin Meyer at Laminar Research per Section 6.7.4. Validate in a beta build if accepted. Exit: a written answer either way. The project is not blocked on the outcome. | 2-4 days |

Total estimate: 45 to 73 developer-days plus 6 to 12 days of artwork. Phases 0 through 2 deliver standalone training value and should be completed and used before committing to the rest. If the project stops after Phase 3, it remains a worthwhile aircrew trainer.

### 8.1 Sequencing

Resist building the network layers first. They are the most visible and the most fun to design, but a beautifully networked exercise around an unconvincing direction finder trains nothing. The engine in Phase 1 is where the training fidelity lives, and the SME validation in Phase 3 is where it is proven.

# 9. Infrastructure and Budget

### 9.1 Workstation requirements

| Item | Minimum | Notes |
| --- | --- | --- |
| GPU | Vulkan 1.3 capable, NVIDIA or AMD, 2 GB VRAM | Intel GPUs are not supported by X-Plane 12. 8 GB VRAM recommended. |
| CPU | 4 or more cores | Modern i5/i7 or Ryzen 5/7 |
| RAM | 8 GB | 16 GB recommended with Air Manager and the bridge alongside |
| Disk | 25 GB minimum | Approaching 60 GB with full global scenery |
| OS | Windows, macOS, or a Debian 12+ derivative, 64-bit | All three are supported by both X-Plane 12 and Air Manager |
| Controls | Yoke or joystick; rudder pedals recommended | Per pilot station |

### 9.2 Server-side services

Services are lightweight; the tracking and scenario services are ordinary Python web applications and the Mumble server is undemanding. Any small VM host or a single cloud instance suffices.

| Service | Resource | Placement |
| --- | --- | --- |
| Scenario service | 1 vCPU, 512 MB | Shared VM |
| Tracking service | 1 vCPU, 1 GB, small database | Shared VM |
| Mumble server | 1 vCPU, 512 MB | Shared VM |
| CalTopo Desktop (if adopted) | Per vendor guidance | Dedicated VM |
| Overlay VPN | Negligible | WireGuard or Tailscale across all participants |

### 9.3 Remote access

Mission base staff participate from home. Rather than exposing training services to the public internet, all participants join an overlay network. This gives every service a stable private address, removes port forwarding, and keeps the exercise network closed.

### 9.4 Budget

Added in v0.2.

Version 0.1 contained no costs. Figures below are order-of-magnitude and must be confirmed against current vendor pricing before any approval request; several are per-seat and scale with the number of stations.

| Item | Basis | Notes |
| --- | --- | --- |
| X-Plane 12 licence | Per pilot workstation | One-time purchase; the free demo suffices for early development but is time-limited per flight |
| Air Manager 5 licence | Per Air Manager workstation | Air Player stations are licensed separately; confirm current per-seat terms |
| CalTopo team account | Annual, per team | Required for API credentials; includes Desktop. The unit or wing may already hold one - a training sub-team may be possible |
| PilotEdge subscription | Per pilot, monthly or annual | ZLA or Western US $19.95/mo or $179/yr each; both areas $34.90/mo or $329/yr. Shared-cockpit occupants cost less: Crew, with full COM transmit, $9.95/mo; Passenger Only $5.95/mo. A three-person crew on one aircraft is therefore roughly $36/mo rather than $60. Five-hour free trial. Confirm current pricing and any organisational terms with the vendor. |
| Flight controls | Per pilot station | Yoke and pedals; the largest hardware cost after the PC |
| Workstations | Per station | Assume members' own PCs where they meet Section 9.1; budget only for shared stations |
| Server hosting | Monthly or existing | Negligible on existing equipment; a small cloud instance otherwise |
| Mumble, WireGuard/Tailscale, XPPython3, Python | - | Free and open source |
| Developer and artist time | Section 8 | Volunteer or otherwise; this is the dominant cost |

# 10. Risks and Constraints

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Nobody owns the system after delivery | High | Name a maintainer before Phase 4. A trainer nobody maintains decays within two sim updates. |
| Training credit not granted, reducing participation | Medium | Raise with wing standardization and NHQ early, before Phase 4. Value as informal practice stands regardless. |
| Cadet participation in an online environment | Medium | Added. If cadets take part remotely, CAP Cadet Protection requirements for electronic communication apply (adult supervision, no one-on-one). Decide early whether cadets are in scope; if so, design the voice net and any messaging accordingly and confirm with the unit's CPP officer. |
| Fidelity criticism from experienced crews | Medium | Position the product as a procedures and decision trainer. Phase 3 SME validation is mandatory, not optional. |
| Artwork never gets done | Medium | Added. Identify the artist in Phase 0. Fall back to a non-copy functional panel if none is available. |
| Vendor faceplate likeness if distributed beyond the unit | Medium | Internal use is unremarkable. Before publishing to the Air Manager community store or sharing across wings, confirm with NHQ. A non-copy faceplate avoids the question. |
| CalTopo Desktop does not serve the APIs | Medium | Phase 4 spike; fall back to a training team account, which is the primary recommendation anyway. |
| Simulated data reaching an operational CalTopo account | Medium | Section 7.4: separate account, separate credentials, distinct callsigns. |
| Air Manager auto-overwrite of modified plugins | Medium | Documented vendor behaviour. Clone before modifying and keep every plugin in git. |
| Official adoption triggers NHQ IT requirements | Low-Medium | Added. As a unit-level training aid on members' equipment, none expected. If it becomes a wing or national program, expect questions about hosting, data handling and member records. Design so that moving the services is easy. |
| PilotEdge dependency for scenario C-1 | Low-Medium | Live ATC is optional. Scenarios degrade to uncontrolled-airspace variants if PilotEdge is unavailable or outside coverage hours. Coordinate staffing in advance for observed exercises; the unit has an existing relationship with PilotEdge to build on. |
| Split-COM transmit not achievable | Low | Section 6.7 options A and B deliver the training value without it. Option C is an investigation, not a dependency. Section 6.7.4 pursues a vendor fix in parallel; a decline costs the project nothing. |
| Ubuntu 26.04 newer than Air Manager's Debian 12 baseline | Low | Dependency script may reference renamed packages. Resolvable in Phase 0. |
| XPPython3 or X-Plane update breaks the plugin | Low | Pin versions; test on sim upgrade; the plugin is small. |
| Scope growth into a full mission simulator | Medium | Phase gates. Stop and use the product after Phase 2 before continuing. Section 6.6 draws the line at shared sim worlds. |

# 11. Decisions Required

The following must be answered before or during Phase 0. Each changes downstream work.

| # | Question | Why it matters |
| --- | --- | --- |
| 1 | Which aircraft and avionics do your crews actually fly - 172 or 182, G1000 or conventional? | Determines whether the DF panel stands alone or must sit alongside a simulated G1000 layout |
| 2 | Is the RT-600 in scope, and can its operating documentation be obtained? | One additional faceplate; blocked without the manual |
| 3 | Is any form of training credit being sought - specifically, may a SET sign off which tasks on the basis of a simulator session? | Determines fidelity, documentation rigour, and whether the session-record work in 12.9 is needed |
| 4 | Is a CalTopo team account available, and can a training team or sub-team be provisioned? | Gates Section 7 |
| 5 | Will this be shared beyond your unit? | Triggers the faceplate likeness question and raises the documentation bar |
| 6 | Are cadets in scope as participants? | Engages Cadet Protection requirements for the online environment |
| 7 | Who will do the artwork? | Not a coding task; unbudgeted in v0.1 |
| 8 | Who authors scenarios, and for which area? | Scenario content is ongoing work; terrain-specific scenarios for the unit's own area are the most valuable |
| 9a | Which PilotEdge coverage area does the operating area need: ZLA, Western US, or both? | Doubles the per-pilot subscription cost if both are required |
| 9c | Who owns the Laminar Research relationship and will author the dataref request? | Section 6.7.4 depends on a named person with the existing contact, not on the development team generally |
| 9b | Which MO radio option is primary: COM2 to ATC, or the CAP FM mission radio? | Determines whether the MO panel routes to PilotEdge or to Mumble (Section 6.7) |
| 9 | How many concurrent stations must Mode C support? | Sizes the service tier and the radio server |
| 10a | Who is the Executive Sponsor, by name? | Section 12.2 - needs standing to make a decision stick, and must be an individual rather than a position |
| 10b | Who is the Project Officer, and who is the deputy? | The one role that cannot be shared or go quiet (12.6, 12.7) |
| 10c | Who deputises for the DF Engine Developer? | The highest bus-factor risk in the project (12.7) |
| 10 | Who owns the system after delivery? | See the first risk in Section 10 |
| 11 | What budget approval path applies? | Section 9.4 items are per-seat; the approval route differs for squadron and wing funds |

# 12. Project Organization and Roles

### 12.1 Governing principle: stage the organization

Added in v0.6.

The most common way a volunteer technical project fails is not lack of people. It is standing up a full organization chart before there is anything to organize - a steering group meeting monthly about a product that does not exist, roles filled by willing people with nothing yet to do, and enthusiasm spent on governance instead of on the work. Six months later the project is remembered as something that had a lot of meetings.

Phases 0 to 2 need four people. The full structure below is what the project grows into by Phase 5, not what it starts with. Section 12.5 says who is needed when. Recruit against that column, not against the whole chart.

### 12.2 Governance

| Role | Accountable for | Notes |
| --- | --- | --- |
| Executive Sponsor | The "why". Owns the business case, secures resources and top cover, unblocks what the Project Officer cannot, and decides whether the project continues at each phase gate. | Wing/CC, Vice/CC or Wing/DO level. Must be a named individual with the standing to make a decision stick, not a position filled by rotation. Deliberately not involved day to day. |
| Project Officer | Delivery. Single accountable person for scope, schedule, risk and reporting. Chairs the phase-gate reviews, owns the plan document, speaks for the project. | The pivotal role. Everything else can be shared; this cannot. Needs enough technical literacy to challenge the developers and enough ES credibility to be heard by aircrew. |
| Steering Group | Phase-gate decisions only: continue, adjust, or stop. | Three to five people: Sponsor, Project Officer, Wing/ES or DO, Stan/Eval representative, one senior Mission Pilot. Meets at gates, not on a calendar. If it becomes a status meeting it has failed. |

### 12.3 Delivery teams

#### Technical leadership

| Role | Accountable for | Skills |
| --- | --- | --- |
| Technical Lead | Architecture, the dataref contract between engine and panels, code standards, the git repository, and technical decisions the Project Officer should not have to make. | Software architecture; enough aviation to reason about the domain. May be the same person as the Project Officer through Phase 2, but the roles should separate by Phase 3. |

#### Team A - Simulation and Instruments (Phases 1-3)

| Role | Accountable for | Skills |
| --- | --- | --- |
| DF Engine Developer | The XPPython3 propagation plugin: bearing, radio horizon, terrain probing, signal model, 406 burst cadence, multipath and the rest of the effects catalogue. Publishes the cap/df/* datarefs. | Python; comfort with geodesy and a little RF intuition. The highest-skill and highest-risk role in the project. |
| Instrument Developer | Air Manager plugins: Becker 517 head, RT-600 head, Mission Observer COM panel, instructor panel. Controls, pages, modes, squelch, audio. | Lua; patience with a vendor API and a GUI editor. |
| Graphic Artist | Faceplate artwork: bezels, knobs, needles, display fonts, preview images. | Vector illustration. A different skill from coding and usually a different person. Works in bursts, not continuously. |

#### Team B - Network and Infrastructure (Phases 4-5)

| Role | Accountable for | Skills |
| --- | --- | --- |
| Services Developer | Scenario service (beacon truth), tracking service, the sim bridge, CalTopo integration, scoring and track recording. | Python, web APIs, a little database work. |
| Mission Base Client Developer | The browser client: live map, alert intake, bearing log, sortie board, retasking, debrief replay. | Front-end web. May be the same person as the Services Developer at first; should not be by Phase 5. |
| Infrastructure and Comms Officer | Hosting, the overlay VPN, the Mumble server and channel structure, audio-routing setup checklists, CalTopo training instance, PilotEdge account administration. | Sysadmin and networking. Unglamorous, continuously needed, and the role most often left unfilled. |

#### Team C - Content and Training (Phase 3 onward)

| Role | Accountable for | Skills |
| --- | --- | --- |
| Scenario Author / Curriculum Lead | The scenario library, mapping scenarios to training objectives, the syllabus, and the instructor's brief for each scenario. Owns what the product actually teaches. | ES and training background. Not a coding role - and arguably the role with the most influence on whether the trainer produces competent searchers. |
| Exercise Instructors | Running sessions, briefing and debriefing crews, feeding observations back into scenario design. | Any qualified instructor. Two or three to start; grows as the trainer spreads. |
| Skills Evaluation Trainers (SETs) | The same session work, plus the authority that matters: a SET can sign off tasks for qualification. If the trainer is ever approved for task credit, SETs are the mechanism by which that credit reaches a member's record. They also define what evidence a simulator session must produce to support a sign-off. | Current SET qualification. Engage at least one SET from Phase 3, well before any credit decision - their view on what a defensible sign-off looks like should shape the debrief and recording design, not be retrofitted to it. |
| Documentation Lead | Station setup checklists, instructor guide, student guide, troubleshooting notes, the plan document itself as it evolves. | Technical writing. Prevents every participant rediscovering the same audio-routing problem. |

### 12.4 Assurance and liaison

These are part-time advisory roles. None is a full-time commitment; all are load-bearing.

| Role | Accountable for | When |
| --- | --- | --- |
| SME Validation Panel | Rating each signal effect against their own flying experience and signing off the effects catalogue before any trainee uses it. Two or three experienced Mission Pilots. | Phase 3 gate; a mandatory exit criterion |
| Stan/Eval Liaison | The training-credit question, put precisely: may a SET sign off which specific tasks, on the basis of a simulator session, and under what conditions? That is a sharper question than "does this count", and it is the one that determines the documentation and evidence standard the system must meet. | Engage before Phase 4, with a SET present. The answer changes how much rigour is justified. |
| Safety Officer | Reviewing the separation between exercise and operational systems: SIM callsigns, CalTopo isolation, credential handling. | Phase 4 review |
| Cadet Protection Officer | Only if cadets participate. Online-environment requirements for the voice net and any messaging. | Before any cadet participation |
| Vendor Liaison | The PilotEdge and Laminar Research relationships: exercise coordination, the dataref request, and testing offers. | Throughout. Must be the named person who actually holds the relationships. |
| Sustainment Owner | The product after delivery: sim and vendor updates, scenario upkeep, onboarding new instructors, keeping the repository alive. | Named before Phase 4 begins - see 12.9 |

### 12.5 Who is needed when

| Role | P0 | P1 | P2 | P3 | P4 | P5 | After |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Executive Sponsor | Yes | Gate | Gate | Gate | Gate | Gate | Hand-off |
| Project Officer | Yes | Yes | Yes | Yes | Yes | Yes | Hand-off |
| Technical Lead | = PO | = PO | = PO | Yes | Yes | Yes | Advisory |
| DF Engine Developer | Yes | Yes | Yes | Yes | - | - | Advisory |
| Instrument Developer | - | - | Yes | Yes | - | - | Advisory |
| Graphic Artist | Identify | - | Yes | Yes | - | - | - |
| Services Developer | - | - | - | - | Yes | Yes | Advisory |
| Mission Base Client Dev | - | - | - | - | Yes | Yes | - |
| Infrastructure and Comms | - | - | - | - | Yes | Yes | Yes |
| Scenario Author | - | - | Consult | Yes | Yes | Yes | Yes |
| Exercise Instructors | - | - | - | Yes | Yes | Yes | Yes |
| Skills Evaluation Trainer (SET) | - | - | Consult | Yes | Yes | Yes | Yes |
| Documentation Lead | - | - | - | Consult | Yes | Yes | Yes |
| SME Validation Panel | - | - | - | Yes | - | - | Periodic |
| Stan/Eval Liaison | Consult | - | - | Yes | Yes | - | Periodic |
| Safety Officer | - | - | - | - | Yes | - | Periodic |
| Vendor Liaison | Yes | - | - | Yes | Yes | Yes | Yes |
| Sustainment Owner | - | - | - | Identify | Named | Shadow | Owns |

The Phase 0-2 team is four people: Sponsor (occasional), Project Officer who is also Technical Lead, DF Engine Developer, and a Graphic Artist working in bursts. Everything else is recruited as the phase that needs it approaches.

### 12.6 Honest time commitments

Volunteers leave projects that ask for more than they were told. These are the figures to quote when recruiting.

| Role | During active phases | Shape of the work |
| --- | --- | --- |
| Executive Sponsor | ~1 hour / month | Gate reviews and the occasional unblocking conversation |
| Project Officer | 4-6 hours / week | Continuous; the one role that cannot go quiet |
| Technical Lead | 4-8 hours / week | Heavier at phase starts, lighter mid-phase |
| DF Engine Developer | 6-10 hours / week | Concentrated in Phases 1 and 3 |
| Instrument Developer | 4-8 hours / week | Phases 2 and 3 |
| Graphic Artist | 3-6 days total | Two bursts, one per instrument head |
| Services / Client Developers | 6-10 hours / week | Phases 4 and 5 |
| Infrastructure and Comms | 2-4 hours / week | Setup-heavy, then steady low-level upkeep |
| Scenario Author | 3-5 hours / week | Ongoing; continues after delivery |
| Documentation Lead | 2-4 hours / week | Phase 4 onward |
| SME Validation Panel | 4-6 hours each, once | A single concentrated session plus follow-up |
| Stan/Eval, Safety, CPP | 1-2 hours / month | Review and advice |
| Sustainment Owner | 2-4 hours / month | Indefinite. The commitment people underestimate. |

### 12.7 Single points of failure

Every role in a volunteer project is one job change, one deployment or one loss of interest away from vacant. Three positions would actually stop the project:

| Position | If it goes vacant | Mitigation |
| --- | --- | --- |
| DF Engine Developer | The core of the product becomes unmaintainable. Nobody else understands the propagation model. | Deputy from Phase 1, even a shadow who only reviews commits. Comment the model heavily and document the physics in the repository, not just the code. |
| Project Officer | The project stalls quietly and nobody notices for two months. | Named deputy Project Officer from Phase 2. Keep the plan document current so the role is recoverable by someone else. |
| Vendor Liaison | The PilotEdge and Laminar relationships are personal, not institutional. They do not transfer automatically. | Introduce a second person into both relationships before Phase 4. Record what was agreed, in writing, in the repository. |

Every other role should have a named deputy by the phase in which it becomes active. The deputy's only obligation before that is to know enough to take over.

### 12.8 Cadence and reporting

| Event | Frequency | Purpose |
| --- | --- | --- |
| Phase-gate review | End of each phase | Steering Group decides continue, adjust or stop against the phase exit criterion. The only formal decision point. |
| Delivery stand-up | Fortnightly, 30 min | Active contributors only. Blockers and hand-offs, not status theatre. |
| Sponsor update | Monthly, written | One page from the Project Officer: progress, risks, decisions needed. Written, so it survives a missed meeting. |
| SME validation session | Phase 3, once | Effects catalogue signed off or sent back. |
| Demonstration | End of Phases 2 and 5 | People fly it. Nothing else generates support like putting a leader in the left seat. |

The demonstration at the end of Phase 2 is the single highest-value governance event in the plan. A working single-seat trainer that a Wing leader can sit down and fly will do more for the project's standing than any number of status reports.

### 12.9 Evidence for sign-off

Added in v0.7.

If Stan/Eval and NHQ do permit task credit, the sign-off has to rest on something a SET can defend. The trainer already produces most of it as a by-product: the recorded track, the bearing log, the reports passed to base, the timing from first signal to overhead, and the debrief replay against beacon truth. What it does not yet produce is a session record - a per-crew, per-scenario summary a SET could attach to a sign-off.

Adding that is cheap if it is designed in during Phase 4 alongside the tracking service, and awkward if it is bolted on afterwards. The Phase 3 SET consultation exists to establish what such a record would need to contain before the recording design is fixed. Note that this is contingency work: it costs little, and it is wasted only if no credit is ever sought.

### 12.10 Sustainment

The first risk in Section 10 is that nobody owns the system after delivery. That risk is managed here or not at all.

| Control | Detail |
| --- | --- |
| Named owner before Phase 4 | Not "the ES section" - a person, who has agreed, in writing, with a stated commitment of 2-4 hours a month |
| Shadow period | The Sustainment Owner participates through Phase 5 rather than receiving a hand-off at the end |
| Everything in version control | Plugins, scenarios, services, documentation and this plan. A repository the Wing controls, not a personal account. |
| Update-cycle drill | The trainer must survive an X-Plane, Air Manager or PilotEdge update. Rehearse this once during Phase 5 so the runbook exists before it is needed. |
| Instructor cadre of at least three, including one SET | A single instructor is a scheduling constraint and a succession risk. Without a current SET in the cadre, any task-credit approval becomes unusable in practice. |
| Annual review | Steering Group reconvenes once a year to decide whether the trainer is still earning its keep, and retires it deliberately if not |

# Appendix A - Reference Sources

| Topic | Source |
| --- | --- |
| Becker SAR-DF 517 quick reference | al005.cap.gov/media/cms/BECKER517QuickRef_F7D3C901A2DD7.pdf |
| SAR-DF 517 installation and operation manual | washingtoncounty.cap.gov/media/cms/Becker_SARDF_517_Manual_E696A5229F5E0.pdf |
| Prosecuting 406 MHz distress beacons | gocivilairpatrol.com/programs/emergency-services/operations-support/prosecuting-406mhz-distress-beacons |
| Electronic search with the Becker and G1000 | rhothetaint.com/wp-content/uploads/2019/08/beckerdfwithg1000slides.pdf |
| Air Manager 5 user manual and plugin structure | docs.siminnovations.com/air_manager_5/user_manual/ |
| Air Manager development API | docs.siminnovations.com/development/api/ |
| Air Manager system requirements | docs.siminnovations.com/air_manager_5/system_requirements/ |
| XPPython3 - datarefs, scenery probe, UDP RREF | xppython3.readthedocs.io |
| CalTopo supported Team API | training.caltopo.com/all_users/team-accounts/teamapi |
| CalTopo live tracks for locators | blog.caltopo.com/2022/04/21/live-tracks-for-locators-and-trackable-devices/ |
| CalTopo live tracking and locators | training.caltopo.com/all_users/share/live-tracking |
| CalTopo Desktop | training.caltopo.com/all_users/desktop |
| caltopo_python (NCSSAR) | github.com/ncssar/caltopo_python |
| X-Plane 12 system requirements | x-plane.com/desktop/try-it/ |
| PilotEdge platform support | pilotedge.net/pages/how-it-works |
| PilotEdge pricing and shared-cockpit tiers | pilotedge.net/pages/pricing |
| PilotEdge operating hours and service area | pilotedge.net/pages/operating-hours-and-service-area |
| PilotEdge Western US expansion | pilotedge.net/pages/western-expansion |
| PilotEdge COM1/COM2 transmit selection | forums.pilotedge.net - audio_panel_out values 6 and 7 |

# Appendix B - Glossary

| Term | Meaning |
| --- | --- |
| AFRCC | Air Force Rescue Coordination Center, which tasks CAP on distress beacon alerts |
| AGL / MSL | Above ground level / mean sea level |
| Burst | The short digital transmission a 406 MHz beacon sends roughly every 50 seconds |
| Cone of confusion | Region above a transmitter where bearing information becomes indeterminate |
| Dataref | A named X-Plane variable exposing simulator state to plugins and external programs |
| DF | Direction finder |
| DREF / RREF | X-Plane UDP messages for writing a dataref and subscribing to dataref values |
| ELT | Emergency locator transmitter |
| Homer | The continuous 121.5 MHz signal most 406 beacons also transmit for final homing |
| Homing | Flying directly toward a signal source using relative bearing |
| MP / MO / MS | Mission Pilot / Mission Observer / Mission Scanner |
| Multipath | Reception of a reflected signal producing a false bearing |
| Radio horizon | Maximum line-of-sight range, approximately 1.23 x sqrt(height in feet) nautical miles |
| Squelch | Threshold below which received signal is suppressed |
| PilotEdge | Subscription network providing live human ATC to flight simulators across the western United States |
| Laminar Research | Developer of X-Plane; Austin Meyer is co-founder |
| Split COM | Audio panel mode allowing pilot and copilot to transmit on different radios simultaneously |
| SET | Skills Evaluation Trainer; a member qualified to sign off tasks for qualification |
| V-SAR | Virtual Search and Rescue; the name of this project |
| ZLA / ZOA | Los Angeles / Oakland Air Route Traffic Control Center |
| XPPython3 | A plugin that lets X-Plane 12 plugins be written in Python |

End of document. CAP V-SAR, version 0.7 draft, 6 September 2026. Paragraphs marked "Changed / Added / Revised" identify revisions from the preceding version.